## Sheet1
	March 19	March 26	April 2	April 9	April 16	April 23	April 30	Mai 7	Mai 14	Mai 21	Mai 28	June 4	June 11	June 18	June 25
Project Planning:
Architecture, Project plan, general and individual work packages, hardware research and orders	TEAM
Project Implementation:
Setup
Hardware setup and testing					TEAM
Design and creation of the case						Luong
Setup VM & Connect Gaming Board						Sandler
Coding
Implement input logic / (Detect Sensor inputs, process inputs, test output/response)							Sandler
Implement game selection logic / (Selection between multiple games, use processed inputs)							Luong
Implement output logic / (Display the game selection, feedback for input on dispaly)									Sandler
Implement AI API functionality and connection									Luong
Implement TicTacToe											Sandler
Implement 4-Gewinnt											Luong
Testing, bug fixing, quality improvments													TEAM
Project Documentation and Presentation:
Documentation														TEAM
Presentation															TEAM